## Summary
IEC-CAS Report-BU
IEC | # CAS to be Initiated (YTD) | # CAS Initiated (YTD) | CAS Received (YTD) | CAS initiated % | CAS received % | CAS Score
CS | 106 | 83 | 25 | 78.3% | 30.12% | 5.9667
BSC | 19 | 18 | 6 | 94.74% | 33.33% | 5.5
TC | 12 | 12 | 12 | 100% | 100% | 5.9
MM | 24 | 24 | 16 | 100% | 66.67% | 6.8
PAI | 8 | 8 | 5 | 100% | 62.5% | 5.75
RMSI | 4 | 4 | 0 | 100% | 0% | 0
BPP | 2 | 2 | 2 | 100% | 100% | 5.5
Centrifugation | 1 | 1 | 1 | 100% | 100% | 7
WAI | 2 | 2 | 1 | 100% | 50% | 7
Total | 178 | 154 | 68 | 86.52% | 44.16% | 5.4907
IEC-CAS Report-Month
| Total No of CASs to be Initiated | No of CASs Initiated | CAS Received | CAS initiated % | CAS received % | CAS Score
Jan | 31 | 18 | 9 | 58.06% | 50% | 6.1
Feb | 28 | 17 | 10 | 60.71% | 58.82% | 6.3
Mar | 41 | 41 | 12 | 100% | 29.27% | 5.9
April | 12 | 12 | 5 | 100% | 41.67% | 6
May | 22 | 22 | 16 | 100% | 72.73% | 6
June | 44 | 44 | 16 | 100% | 36.36% | 6
July | 12 | 12 | 2 | 100% | 16.67% | 5
Aug | 3 | 3 | 1 | 100% | 33.33% | 5
Sep | 22 | 22 | 3 | 100% | 13.64% | 6
Total | 215 | 191 | 74 | 88.84% | 38.74% | 5.8111

## Sheet1
Vendor | (All) |  |  | Row Labels | Average of Jan CAS Score | Average of Feb CAS Score | Average of Mar CAS Score | Average of Apr CAS Score | Average of May CAS Score | Average of June CAS Score | Average of July CAS Score | Average of Aug CAS Score | Average of Sep CAS Score
|  |  |  | BPP |  | 5 | 6
Row Labels | Sum of No of CFBs to be Initiated (YTD) | Sum of No of CFBs | Sum of CFB Received | BSC | 6 |  | 5.5 |  |  | 5.3333
CS | 119 | 96 | 27 | Centrifugation |  |  |  |  | 7
BSC | 19 | 18 | 6 | CS | 5.5 | 6 | 5.8571 | 6.4 | 6 | 6.5 | 6 | 5 | 6
MM | 24 | 24 | 16 | MM | 7 | 7 | 7 |  | 6.6 | 6 | 4
TC | 12 | 12 | 12 | PAI | 6 |  | 5.5 |  | 5 | 6
PAI | 9 | 9 | 6 | RMSI
RMSI | 5 | 5 |  | TC | 6 | 6 |  |  | 6.25 | 5.6667
WAI | 3 | 3 | 1 | WAI | [5 empty] | 7
BPP | 2 | 2 | 2 | (blank)
Centrifugation | 1 | 1 | 1 | Grand Total | 6.2222 | 6.3 | 5.8462 | 6.4 | 6.25 | 5.875 | 5 | 5 | 6
Grand Total | 194 | 170 | 71
Row Labels | Sum of No of CFBs to be Initiated (YTD) | Sum of No of CFBs | Sum of CFB Received
Cyient | 44 | 32 | 9
CS | 33 | 21 | 3
BSC | 2 | 2 | 1
MM | 9 | 9 | 5
Grand Total | 44 | 32 | 9

## Consolidated Report
[13 empty] | Jan | [5 empty] | Feb | [5 empty] | Mar | [5 empty] | April | [5 empty] | May | [5 empty] | June | [5 empty] | July | [5 empty] | Aug | [5 empty] | Sep | [5 empty] | Oct | [5 empty] | Nov | [5 empty] | Dec
Vendor | BU | Category | Program | Category | Intiated | Project | Proj Leader | No of CFBs to be Initiated (YTD) | No of CFBs Initiated YTD | CFB Received YTD | Initiation% | Received% | CFBs to be Initiated Jan | CFBs Initiated Jan | CF Status | Requested date | received date | Jan CAS Score | CFBs to be Initiated Feb | No of CFBs Initiated Feb | CF Status | Requested date | received date | Feb CAS Score | CFBs to be Initiated Mar | No of CFBs Initiated Mar | CF Status | Requested date | received date | Mar CAS Score | No of CFBs to be Initiated April | No of CFBs Initiated April | CF Status | Requested date | received date | Apr CAS Score | No of CFBs to be Initiated May | No of CFBs Initiated May | CF Status | Requested date | received date | May CAS Score | No of CFBs to be Initiated June | No of CFBs Initiated June | CF Status | Requested date | received date | June CAS Score | No of CFBs to be Initiated July | No of CFBs Initiated July | CF Status | Requested date | received date | July CAS Score | No of CFBs to be Initiated Aug | No of CFBs Initiated Aug | CF Status | Requested date | received date | Aug CAS Score | No of CFBs to be Initiated Sep | No of CFBs Initiated Sep | CF Status | Requested date | received date | Sep CAS Score | No of CFBs to be Initiated Oct | No of CFBs Initiated Oct | CF Status | Requested date | received date | Oct CAS Score | No of CFBs to be Initiated Nov | No of CFBs Initiated Nov | CF Status | Requested date | received date | Nov CAS Score | No of CFBs to be Initiated Dec | No of CFBs Initiated Dec | CF Status | Requested date | received date | Dec CAS Score
iLensys | CS | CAD | CAD | S1 | Monthly | Availability & Electrical | Harish | 6 | 6 | 1 | 100% | 16.67% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Initiated | 2015-02-26 |  |  | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Received | 2015-06-08 | 2015-06-09 | 6 | 1 | 1 | Initiated | 2015-07-10
iLensys | CS | CAD | CAD | S1 | Monthly | CAT | Harish | 7 | 7 | 4 | 100% | 57.14% | 1 | 1 | Received | 2015-02-06 | 2015-02-06 | 6 | 1 | 1 | Received | 2015-02-26 | 2015-02-26 | 6 | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Received | 2015-05-13 | 2015-05-18 | 6 | 1 | 1 | Received | 2015-06-08 | 2015-06-09 | 7 | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | CAD | CAD | S1 | Monthly | E-Hero | Harish | 8 | 8 | 1 | 100% | 12.5% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Initiated | 2015-02-26 |  |  | 1 | 1 | Received | 2015-03-30 | 2015-04-14 | 6 | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12 | [8 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | CAD | CAD | S1 | Monthly | E-Warrior | Harish | 8 | 8 | 4 | 100% | 50% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Received | 2015-02-26 | 2015-02-26 | 4 | 1 | 1 | Received | 2015-03-30 | 2015-04-14 | 5 | 1 | 1 | Received | 2015-05-13 | 2015-05-13 | 6 | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12 | [8 empty] | 1 | 1 | received | 2015-09-30 | 2015-10-13 | 6
iLensys | CS | CAD | CAD | S1 | Monthly | VHEN | Harish | 7 | 7 |  | 100% | 0% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Initiated | 2015-02-26 |  |  | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | CAD | CAD | S1 | Monthly | Quality | Harish | 2 | 2 |  | 100% | 0% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Initiated | 2015-02-26
iLensys | CS | Techpub | Techpub | S1 | Monthly | Techpub | Santa | 7 | 7 | 1 | 100% | 14.29% | 1 | 1 | Initiated | 2015-02-06 |  |  | 1 | 1 | Initiated | 2015-02-26 |  |  | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Received | 2015-06-08 | 2015-06-08 | 6 | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | Data Analytics | Data Analytics | S1 | Monthly | PEEK Service | Chakri | 7 | 6 | 5 | 85.71% | 83.33% | 1 | [5 empty] | 1 | 1 | Received | 2015-02-26 | 2015-02-27 | 7 | 1 | 1 | Received | 2015-03-30 | 2015-03-30 | 7 | 1 | 1 | Received | 2015-05-13 | 2015-05-15 | 7 | 1 | 1 | Received | 2015-06-08 | 2015-06-08 | 7 | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12 | 2015-08-12 | 6
iLensys | CS | Data Analytics | Data Analytics | S1 | Monthly | E-Hero | Chakri | 7 | 6 | 3 | 85.71% | 50% | 1 | [5 empty] | 1 | 1 | Received | 2015-02-26 | 2015-02-27 | 7 | 1 | 1 | Received | 2015-03-30 | 2015-03-30 | 6 | 1 | 1 | Received | 2015-05-13 | 2015-05-15 | 7 | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | Data Analytics | Data Analytics | S1 | Monthly | Life test | Chakri | 7 | 6 |  | 85.71% | 0% | 1 | [5 empty] | 1 | 1 | Initiated | 2015-02-26 |  |  | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12 | [8 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | IDO | IDO | S1 |  | E-Warrior | Mallikarjun | 2 |  |  | 0% |  | 1 | [5 empty] | 1
Cyient | CS | Availability | Availability | S2 | Monthly | Availability-Projects | Surendra | 7 | 5 |  | 71.43% | 0% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | MCTO | MCTO | S2 | Monthly | MCTO-Projects | Chakri | 7 | 5 | 1 | 71.43% | 20% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 |  |  | 1 | 1 | Initiated | 2015-05-13 |  |  | 1 | 1 | Received | 2015-06-08 | 2015-06-09 | 4 | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
Cyient | CS | Vitality | Vitality | S3 | Monthly | VHEN-Vitality | Rajesh | 6 | 4 | 1 | 66.67% | 25% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Received | 2015-03-30 | 2015-04-22 | 6 | [6 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
Cyient | CS | Vitality | Vitality | S3 | Monthly | E-Warrior-Cyient | srikanth | 5 | 3 |  | 60% | 0% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 | [8 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10
TechM | CS | Vitality | Vitality | S3 | Monthly | E-Warrior-TechM | Zameer | 5 | 3 | 2 | 60% | 66.67% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Received | 2015-03-30 | 2015-04-07 | 4 | [6 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Received |  | 2015-06-19 | 6
Cyient | CS | Vitality | Vitality | S3 | Monthly | Smart Trac | Sachin | 5 | 3 | 2 | 60% | 66.67% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Received | 2015-03-30 | 2015-04-20 | 7 | [6 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 | 2015-07-10 | 7
TechM | CS | Quality | CAT | S3 | Monthly | CAT | Santhosh | 6 | 4 | 1 | 66.67% | 25% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 |  |  |  |  | Received |  |  | 6 | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10 |  |  | 1 | 1 | Initiated | 2015-08-12
iLensys | CS | Special project | Special project | S1 | One time | Endurance - Video | Sravani | 1 | 1 | 1 | 100% | 100% | 1 | 1 | Received |  |  | 5
iLensys | MM | CAD | Adelaide | S1 | Quarterly | Work done in Q1 | Vinay | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Received | 2015-04-21 | 2015-04-22 | 7
iLensys | MM | CAD | WIL | S1 | Quarterly | Work done in Q1 | Vinay | 2 | 2 | 2 | 100% | 100% | [6 empty] | 1 | 1 | Received | 2015-02-17 | 2015-02-28 | 7 | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-07 | 7
iLensys | MM | Availability | WIL | S1 | Quarterly | Work done in Q1-Availability | Vinay | 2 | 2 | 2 | 100% | 100% | [6 empty] | 1 | 1 | Received | 2015-02-17 | 2015-02-28 | 7 | 1 | 1 | Initiated | 2015-04-24 | [10 empty] | Received |  | 2015-05-02 | 7
iLensys | MM | CAD | MIN | S1 | Quarterly | Work done in Q1 | Vinay | 1 | 1 |  | 100% | 0% | [12 empty] | 1 | 1 | Initiated | 2015-04-21
iLensys | MM | CAD | ECB | S1 | Quarterly | Work done in Q1 | Vinay | 2 | 2 | 1 | 100% | 50% | [6 empty] | 1 | 1 | Received |  | 2015-02-17 | 7 | 1 | 1 | Initiated | 2015-04-21
iLensys | MM | Availability | ECB | S1 | Quarterly | Work done in Q1-Availability | Vinay | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Initiated | 2015-04-24 | [10 empty] | Received |  | 2015-05-12 | 6
iLensys | MM | IDO | IDO | S1 | One time | WP-1026 (Completed) | Mallikarjun | 1 | 1 | 1 | 100% | 100% | [6 empty] | 1 | 1 | Received | 2015-02-04 | 2015-02-17 | 7
iLensys | MM | CAD | Adelaide | S1 | Quarterly | Work done in Q2 | Vinay | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-10
iLensys | MM | CAD | WIL | S1 | Quarterly | Work done in Q2 | Vinay | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Received | 2015-07-10 | 2015-07-13 | 7
iLensys | MM | Availability | WIL | S1 | Quarterly | Work done in Q2-Availability | Vinay | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Received | 2015-07-10 | 2015-07-13 | 7
iLensys | MM | CAD | MIN | S1 | Quarterly | Work done in Q2 | Vinay | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Received | 2015-07-10 | 2015-07-15 | 4
iLensys | MM | CAD | ECB | S1 | Quarterly | Work done in Q2 | Vinay | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-10
Cyient | MM | CAD | Willmington | S1 |  | Schematic layout development | Srikanth G | 2 | 2 | 2 | 100% | 100% | 1 | 1 | Received | 2015-01-09 | 2015-01-16 | 7 | [6 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-07 | 6
Cyient | MM | CAD | Willmington | S1 |  | Schematic layout development | Srikanth G | 2 | 2 | 1 | 100% | 50% | 1 | 1 | Received | 2015-01-09 | 2015-01-16 | 7 | [24 empty] | 1 | 1 | Initiated | 2015-07-21
Cyient | MM | CAD | Adelaide | S1 |  | PCAD to Altum conv | Srikanth G | 3 | 3 | 2 | 100% | 66.67% | 1 | 1 | Received | 2015-01-13 | 2015-01-13 | 7 | [6 empty] | 1 | 1 | Initiated | 2015-04-21 | [14 empty] | 1 | 1 | Initiated | 2015-07-21 |  |  |  |  | Received |  | 2015-08-04 | 4
Cyient | MM | Vitality | Vitality | S3 |  | Minizap30 | Srikanth G | 2 | 2 | 1 | 100% | 50% | [12 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-20 | 7 | 1 | 1 | Initiated | 2015-07-21
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO | Vijesh | 2 | 2 | 2 | 100% | 100% | 1 | 1 | Received | 2015-01-12 | 2015-01-06 | 6 | [6 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-05 | 7
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q1 | Vijesh | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-05 | 5
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q1 | Vijesh | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-05 | 7
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q1 | Vijesh | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Initiated | 2015-04-21 | [10 empty] | Received |  | 2015-05-05 | 6
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q2 | Vijesh | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-10 | 2015-07-21 | 6
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q2 | Vijesh | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-10 | 2015-07-21 | 6
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q2 | Vijesh | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-10 | 2015-07-21 | 4
iLensys | TC | CAD | CAD | S1 | Quarterly | Work Packages/ECR-ECO-Q2 | Vijesh | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-10 | 2015-07-21 | 6
iLensys | TC | Availability | Availability | S1 |  | Component Management | Vijesh | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-21 |  | 6
iLensys | TC | CAD |  | S1 | One time | Work done on VT Cart | Vinay/Vijesh | 1 | 1 | 1 | 100% | 100% | [6 empty] | 1 | 1 | Received | 2015-02-10 | 2015-02-23 | 6
iLensys | TC | CAD |  |  |  | Digital Manufacturing: TC Versa line- Phase 1 | Vijesh | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Initiated | 2015-04-29 | [16 empty] | Received |  | 2015-06-02 | 6
iLensys | RMSI | CAD | Quality | S1 |  | CAD Support for Q1 | Vijesh | 1 | 1 |  | 100% | [13 empty] | 1 | 1 | Initiated | 2015-04-21
iLensys | RMSI | CAD | Quality | S1 |  | CAD Support for Q2 | Vijesh | 1 | 1 |  | 100% | [31 empty] | 1 | 1 | Initiated | 2015-07-10
iLensys | RMSI | IDO | IDO | S1 |  | EPD-Pheonix Dosimeter | Mallikarjun | 1 | 1 |  | 100% | [13 empty] | 1 | 1 | Initiated | 2015-04-21
iLensys | RMSI | IDO | IDO | S1 |  | EPD-Dosimetre-Desktop reader | Mallikarjun | 1 | 1 |  | 100% | [31 empty] | 1 | 1 | Initiated | 2015-06-26
iLensys | RMSI | CAD |  | S1 |  | Seismic fixture design and analysis | Vinay | 1 | 1 |  | 100% | 0% | [42 empty] | 1 | 1 | Initiated | 2015-08-24
iLensys | PAI | CAD | Quality | S1 | Quarterly | (Work Packages) for Q1 | Vijesh | 1 | 1 |  | 100% | 0 | [12 empty] | 1 | 1 | Initiated | 2015-04-21
iLensys | PAI | CAD | Quality | S1 | Quarterly | (Work Packages) for Q2 | Vijesh | 1 | 1 |  | 100% | 0 | [30 empty] | 1 | 1 | Initiated | 2015-07-21
iLensys | PAI | IDO | IDO | S1 |  | PAI- XL5-CMF | Mallikarjun | 1 | 1 | 1 | 100% | 100% | 1 | 1 | Received | 2014-12-07 | 2015-01-05 | 6
BAT | PAI | Vitality |  |  |  | microPAHZIR EOL | Shirish Kulkarni | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Received | 2015-04-03 | 2015-04-22 | 6
BAT | PAI | CAD |  |  |  | Trunarc-Japanese software release, 1.5 | Uma | 2 | 2 | 2 | 100% | 100% | [24 empty] | 1 | 1 | Received | 2015-05-21 | 2015-05-22 | 5 |  |  | Received |  | 2015-06-03 | 6
BAT | PAI | CAD | CAD | S1 |  | Trunarc-Japanese software release, 1.4.1 | Uma | 1 | 1 | 1 | 100% | 100% | 1 | 1 | Received | 2015-01-19 | 2015-01-19 | 6
iLensys | PAI | IDO | IDO | S1 |  | PAI-LTS | Mallikarjun | 1 | 1 |  | 100% | [13 empty] | 1 | 1 | Initiated | 2015-04-29
iLensys | PAI | User App | User App | S1 |  | PAI-Interactive app | Karthik | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Received | 2015-03-12 | 2015-03-12 | 5
iLensys | BPP | CAD | CAD | S1 |  | BIN Drawings | Vinay | 2 | 2 | 2 | 100% | 100% | [6 empty] | 1 | 1 | Received | 2015-02-17 | 2015-02-18 | 5 | 1 | 1 | Received | 2015-04-17 | 2015-04-17 | 6
Cyient | BSC | CAD | Availaility |  |  | NCAT | Raju Vegesna | 1 | 1 |  | 100% |  | 1 | 1 | Initiated | 2015-01-23
Ilensys | BSC | IDO | IDO | S1 |  | Speed Vac | Mallikarjun | 1 | 1 | 1 | 100% | 100% | 1 | 1 | Received | 2015-11-21 | 2015-01-07 | 6
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos Project | Lovwin | 3 | 2 |  | 66.67% | 0% | 1 | 1 | Initiated |  |  |  | 1 | [11 empty] | 1 | 1 | Initiated | 2015-05-08
Ilensys | BSC | CAD | Availaility | S1 |  | ECN and Agile Requests | Lovwin | 3 | 3 |  | 100% | 0% | 1 | 1 | Initiated |  |  |  | 1 | 1 | Initiated | [21 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-250L Outer Door Cabinet RAL pre Assembly 240L-Q2 | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-Old-New Flaschendreher-Q2 | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-Heaters door left and right 250l Kronos-Q2 | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-HLA Documentation Change Glass Door-Q2 | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-Packaging Parts for the 250l unit | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-Air guide Back wall-Q2 | Lovwin | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Received | 2015-07-15 | 2015-07-16 | 4
Ilensys | BSC | CAD | Vitality | S3 |  | Kronos-Glass Plate drawing updates-Q2 | Lovwin | 1 | 1 |  | 100% | 0% | [30 empty] | 1 | 1 | Initiated | 2015-07-15
Ilensys | BSC | CAD | Vitality | S3 |  | WP-Goulash + Drawing Updates | Lovwin | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-15 | 2015-07-20 | 6
Ilensys | BSC | CAD | Vitality |  |  | Drawing Updates | Lovwin | 1 | 1 | 1 | 100% | 100% | [30 empty] | 1 | 1 | Initiated | 2015-07-15 | 2015-07-20 | 6
Ilensys | WAI | CAD | CAD | S1 |  | WAI | Lovwin | 1 | 1 |  | 100% | [13 empty] | 1 | 1 | Initiated | 2015-03-30
Ilensys | WAI | Techpub | Manuals | S1 |  | WAI | Lovwin | 1 | 1 | 1 | 100% | [25 empty] | 1 | 1 | Initiated | 2015-05-18 |  |  |  |  | Received |  | 2015-06-10 | 7
Ilensys | WAI | CAD |  | S1 |  | WAI | Vijesh | 1 | 1 |  | 100% | [43 empty] | 1 | 1 | Initiated | 2015-08-24
Cyient | BSC | CAD |  |  |  | Helios re-Layout | Raju Vegesna | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Received | 2015-03-27 | 2015-03-29 | 6
Ilensys | BSC | CAD |  |  |  | B2 Cabinets | Lovwin | 1 | 1 | 1 | 100% | 100% | [12 empty] | 1 | 1 | Received | 2015-03-04 | 2015-03-10 | 5
Cyient | CS | Vitality | CAT | S3 | Monthly | Japan Plan B | Surendra | 5 | 3 |  | 60% | 0% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 | [8 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10
Cyient | CS | Vitality | CAT | S3 | Monthly | MDD Classification | Surendra | 5 | 3 |  | 60% | 0% | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | Initiated | 2015-03-30 | [8 empty] | 1 | 1 | Initiated | 2015-06-08 |  |  | 1 | 1 | Initiated | 2015-07-10
iLensys | Centrifugation | CAD | CAD | S1 |  | CAD | Lovwin | 1 | 1 | 1 | 100% | 100% | [24 empty] | 1 | 1 | Received | 2015-05-18 | 2015-05-20 | 7
iLensys | CS | User App | User App | S1 |  | Energy Simulation | Karthik | 1 | 1 | 1 | 100% | 100% | [42 empty] | 1 | 1 | Received | 2015-08-20 | 2015-08-24 | 5
iLensys | BSC | Techpub | Manuals | S1 |  | Cytoperm Manual | Lovwin | 1 | 1 |  | 100% | 0% | [54 empty] | 1 | 1 | Initiated | 2015-10-01
Cyient | MM | Vitality | Vitality | S3 |  | KeytekZap30 | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
Cyient | MM | CAD | Willmington | S1 |  | Schematic layout development | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
Cyient | MM |  |  |  |  | SiLA converter for Ascent fluroscan | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
Cyient | MM | CAD | Adelaide | S1 |  | PCAD to Altum conv | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
Cyient | MM |  |  |  |  | Software sustenance for Gauging systems | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
Cyient | MM |  |  |  |  | Language translator Tool | Srikanth G | [53 empty] | 1 | 1 | Intiated | 2015-09-29
iLensys | CS | Data Analytics | Data Analytics | S1 |  | E-Hero | Chakri | [53 empty] | 1 | 1 | received | 2015-09-30 | 2015-09-30 | 6
iLensys/Cyient | CS | VHEN | VHEN | S2 |  | VHEN Projects | Rajesh B.A | [53 empty] | 1 | 1 | received | 2015-09-30 | 2015-10-08 | 6
TechM | CS | Vitality | Vitality | S3 |  | E-Warrior-TechM - HMI Support | Zameer | [59 empty] | 1 | 1 | Intiated | 2015-10-01
Cyient | CS |  |  | S3 |  | Klatu Support | Sachin | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys/Cyient | CS | Availability | Availability | S2 |  | Availability-Projects | Surendra | [53 empty] | 1 | 1 | Intiated | 2015-09-30
Cyient | CS | Vitality | Vitality | S3 |  | Energy Warrior-Electronics Engineering Support | Srikanth N | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys/Cyient/TehM | CS | CAT | CAT | S2 |  | Customer Allegiance –Quality & Custom Projects | Santhosh | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | CAD | CAT | S1 |  | Customer Allegiance -CAD support | Harish | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | MCTO | MCTO | S2 |  | MCTO Projects | Chakri | [53 empty] | 1 | 1 | Intiated | 2015-09-30
TechM | CS | Vitality | Vitality | S3 |  | Energy Warrior Mechanical & Thermal Engineering Support | Zameer | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | Data Analytics | Data Analytics | S1 |  | E-Hero | Chakri | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | VHEN | VHEN | S1 |  | VHEN-CAD Support | Harish | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | Techpub | Techpub | S1 |  | Technical Publications | Harish | [53 empty] | 1 | 1 | Intiated | 2015-09-30
iLensys | CS | Data Analytics | Data Analytics | S1 |  | PEEK Service – Performance Data Analytics | Chakri | [53 empty] | 1 | 1 | Intiated | 2015-09-30
Note on AU18: Initiated on 7/10/2015 Yet to receive feedback for June month
Note on AH20: Considering Mar Feedback of CAT in May
Note on AP23: Mar Feed back received in May
Note on AP34: Mar Feed back received in May
Note on AB38: Initiated 1 CAS but received 4 feedbacks
Note on AN38: Mar Feedback Received in May
Note on AB39: Initiated 1 CAS but received 4 feedbacks
Note on AN39: Mar Feedback Received in May
Note on AB40: Initiated 1 CAS but received 4 feedbacks
Note on AN40: Mar Feedback Received in May
Note on AB41: Initiated 1 CAS but received 4 feedbacks
Note on AN41: Mar Feedback Received in May
Note on AT77: Received May month Feedback in June

## CS
Month | Vendor | Business Unit | Program | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-01-01 | Ilensys | CS | CAD | S1 | Availability & Electrical | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | CAD | S1 | CAT | Harish | Avl | Received | 2015-02-06 | 2015-02-06 | 6
2015-01-01 | Ilensys | CS | CAD | S1 | E-Hero | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | CAD | S1 | E-Warrior | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | CAD | S1 | VHEN | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | CAD | S1 | Quality | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | TechPub | S1 | TechPub | Harish | Avl | Initiated | 2015-02-06
2015-01-01 | Ilensys | CS | SPECIAL PROJECT | S1 | Endurance - Video | Srvani |  | Received | 2015-01-08 | 2015-01-12 | 5
2015-02-01 | Ilensys | CS | CAD | S1 | Availability & Electrical | Harish | Avl | Initiated
2015-02-01 | Ilensys | CS | CAD | S1 | CAT | Harish | Avl | Received | 2015-02-26 | 2015-02-26 | 6
2015-02-01 | Ilensys | CS | CAD | S1 | E-Hero | Harish | Avl | Initiated
2015-02-01 | Ilensys | CS | CAD | S1 | E-Warrior | Harish | Avl | Received | 2015-02-26 | 2015-02-26 | 4
2015-02-01 | Ilensys | CS | CAD | S1 | VHEN | Harish | Avl | Initiated
2015-02-01 | Ilensys | CS | CAD | S1 | Quality | Harish | Avl | Initiated
2015-02-01 | Ilensys | CS | TechPub | S1 | TechPub | Harish | Avl | Initiated
2015-02-01 | Ilensys | CS | DA | S1 | PEEK Service | Chakri | Avl | Received | 2015-02-26 | 2015-02-27 | 7
2015-02-01 | Ilensys | CS | DA | S1 | E-Hero | Chakri | Avl | Received | 2015-02-26 | 2015-02-27 | 7
2015-03-01 | TechM | CS |  | S3 | CAT | Santhosh |  | Received |  |  | 6
2015-03-01 | Cyient | CS | Vitality | S3 | Japan Plan B | Surendra |  | Initiated
2015-03-01 | Cyient | CS | Vitality | S3 | MDD Classification | Surendra |  | Initiated
2015-03-01 | Cyient | CS | Availability | S2 | Availability | Surendra |  | Initiated
2015-03-01 | Ilensys | CS | MCTO | S2 | MCTO | Chakri |  | Initiated
2015-03-01 | Cyient | CS |  | S3 | VHEN | Rajesh |  | Received |  |  | 6
2015-03-01 | TechM | CS | Vitality | S3 | Energy Warrior-Mechanical | Zameer |  | Received |  |  | 4
2015-03-01 | Cyient | CS | Vitality | S3 | Energy Warrior-Electronics | Srikanth |  | Initiated
2015-03-01 | Cyient | CS | Vitality | S3 | Smart Tracker | Sachin |  | Received | 2015-03-30 | 2015-04-20 | 7
2015-03-01 | Ilensys | CS | CAD | S1 | Availability-CAD | Harish |  | Initiated
2015-03-01 | Ilensys | CS | CAD | S1 | CAT-CAD | Harish |  | Initiated
2015-03-01 | Ilensys | CS | CAD | S1 | E warrior-CAD | Harish |  | Received | 2015-03-30 | 2015-04-14 | 5
2015-03-01 | Ilensys | CS | CAD | S1 | E Hero-CAD | Harish |  | Received | 2015-03-30 | 2015-04-14 | 6
2015-03-01 | Ilensys | CS | CAD | S1 | VHEN-CAD | Harish |  | Initiated
2015-03-01 | Ilensys | CS | TechPub | S1 | TechPub | Harish |  | Initiated
2015-03-01 | Ilensys | CS | DA | S1 | Data Analytics - E Hero | Chakri |  | Received |  |  | 6
2015-03-01 | Ilensys | CS | DA | S1 | Data Analytics - PEEK Service | Chakri |  | Received |  |  | 7
2015-03-01 | Ilensys | CS | DA | S1 | Data Analytics - Life Test | Chakri |  | Initiated
2015-04-01 | Ilensys | CS | CAD | S1 | Availability-CAD | Harish |  | Initiated
2015-04-01 | Ilensys | CS | CAD | S1 | CAT-CAD | Harish |  | Initiated
2015-04-01 | Ilensys | CS | CAD | S1 | E warrior-CAD | Harish |  | Received | 2015-05-13 | 2015-05-15 | 6
2015-04-01 | Ilensys | CS | CAD | S1 | E Hero-CAD | Harish |  | Initiated
2015-04-01 | Ilensys | CS | CAD | S1 | VHEN-CAD | Harish |  | Initiated
2015-04-01 | Ilensys | CS | TechPub | S1 | TechPub | Harish |  | Initiated
2015-04-01 | Ilensys | CS | DA | S1 | Data Analytics - E Hero | Chakri |  | Received | 2015-05-13 | 2015-05-15 | 7
2015-04-01 | Ilensys | CS | DA | S1 | Data Analytics - PEEK Service | Chakri |  | Received | 2015-05-13 | 2015-05-15 | 7
2015-04-01 | Ilensys | CS | DA | S1 | Data Analytics - Life Test | Chakri |  | Initiated
2015-05-15 | Ilensys | CS | CAD | S1 | CAT-CAD | Harish |  | Received |  |  | 6
2015-05-15 | TechM | CS |  | S3 | CAT | Santhosh |  | Initiated | 2015-06-08
2015-05-16 | Cyient | CS | Vitality | S3 | Japan Plan B | Surendra |  | Initiated | 2015-06-08
2015-05-17 | Cyient | CS | Vitality | S3 | MDD Classification | Surendra |  | Initiated | 2015-06-08
2015-05-18 | Cyient | CS | Availability | S2 | Availability | Surendra |  | Initiated | 2015-06-08
2015-05-19 | Ilensys | CS | MCTO | S2 | MCTO | Chakri |  | Received | 2015-06-08 | 2015-06-09 | 4
2015-05-20 | Cyient | CS |  | S3 | VHEN | Rajesh |  | Initiated | 2015-06-08
2015-05-21 | TechM | CS | Vitality | S3 | Energy Warrior-Mechanical | Zameer |  | Initiated | 2015-06-08
2015-05-22 | Cyient | CS | Vitality | S3 | Energy Warrior-Electronics | Srikanth |  | Initiated | 2015-06-08
2015-05-23 | Cyient | CS | Vitality | S3 | Smart Tracker | Sachin |  | Initiated | 2015-06-08
2015-05-24 | Ilensys | CS | CAD | S1 | Availability-CAD | Harish |  | Received | 2015-06-08 | 2015-06-09 | 6
2015-05-25 | Ilensys | CS | CAD | S1 | CAT-CAD | Harish |  | Received | 2015-06-08 | 2015-06-09 | 7
2015-05-26 | Ilensys | CS | CAD | S1 | E warrior-CAD | Harish |  | Initiated | 2015-06-08
2015-05-27 | Ilensys | CS | CAD | S1 | E Hero-CAD | Harish |  | Initiated | 2015-06-08
2015-05-28 | Ilensys | CS | CAD | S1 | VHEN-CAD | Harish |  | Initiated | 2015-06-08
2015-05-29 | Ilensys | CS | TechPub | S1 | TechPub | Harish |  | Initiated | 2015-06-08 | 2015-06-09 | 6
2015-05-30 | Ilensys | CS | DA | S1 | Data Analytics - E Hero | Chakri |  | Initiated | 2015-06-08
2015-05-31 | Ilensys | CS | DA | S1 | Data Analytics - PEEK Service | Chakri |  | Initiated | 2015-06-08 | 2015-06-09 | 7
2015-05-15 | Ilensys | CS | DA | S1 | Data Analytics - Life Test | Chakri |  | Initiated | 2015-06-08
2015-06-15 | TechM | CS | Vitality | S3 | Energy Warrior-Mechanical | Zameer |  | Received |  | 2015-06-19 | 6
2015-06-15 | TechM | CS |  | S3 | CAT | Santhosh |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS | Vitality | S3 | Japan Plan B | Surendra |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS | Vitality | S3 | MDD Classification | Surendra |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS | Availability | S2 | Availability | Surendra |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | MCTO | S2 | MCTO | Chakri |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS |  | S3 | VHEN | Rajesh |  | Initiated | 2015-07-10
2015-06-15 | TechM | CS | Vitality | S3 | Energy Warrior-Mechanical | Zameer |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS | Vitality | S3 | Energy Warrior-Electronics | Srikanth |  | Initiated | 2015-07-10
2015-06-15 | Cyient | CS | Vitality | S3 | Smart Tracker | Sachin |  | Received | 2015-07-10 | 2015-07-10 | 7
2015-06-15 | Ilensys | CS | CAD | S1 | Availability-CAD | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | CAD | S1 | CAT-CAD | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | CAD | S1 | E warrior-CAD | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | CAD | S1 | E Hero-CAD | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | CAD | S1 | VHEN-CAD | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | TechPub | S1 | TechPub | Harish |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | DA | S1 | Data Analytics - E Hero | Chakri |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | DA | S1 | Data Analytics - PEEK Service | Chakri |  | Initiated | 2015-07-10
2015-06-15 | Ilensys | CS | DA | S1 | Data Analytics - Life Test | Chakri |  | Initiated | 2015-07-10
2015-07-15 | iLensys | CS | CAD | S1 | CAD | Harish |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | CAD | S1 | CAD | Harish |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | CAD | S1 | CAD | Harish |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | CAD | S1 | CAD | Harish |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | Techpub | S1 | Techpub | Santa |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | Data Analytics | S1 | Data Analytics | Chakri |  | Initiated | 2015-08-12 | 2015-08-12 | 6
2015-07-15 | iLensys | CS | Data Analytics | S1 | Data Analytics | Chakri |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | Data Analytics | S1 | Data Analytics | Chakri |  | Initiated | 2015-08-12
2015-07-15 | Cyient | CS | Availability | S2 | Availability | Surendra |  | Initiated | 2015-08-12
2015-07-15 | iLensys | CS | MCTO | S2 | MCTO | Chakri |  | Initiated | 2015-08-12
2015-07-15 | Cyient | CS | Vitality | S3 | Vitality | Rajesh |  | Initiated | 2015-08-12
2015-07-15 | TechM | CS | Quality | S3 | CAT | Santhosh |  | Initiated | 2015-08-12
2015-08-15 | iLensys | CS | User App | S1 | Energy Simulation | Karthik |  | Received | 2015-08-20 | 2015-08-24
Note on A46: Mar Feedback received in May

## BSC
Month | Vendor | Business Unit | Program | Category | Project name | project lead | Site | Cutomer | CF Status | Requested date | Received date | CAS Score | Attachments
2015-01-01 | Cyient | BSC | Availaility |  | NCAT | Raju Vegesna | Germany |  | Initiated | 2015-01-23
2015-01-01 | Ilensys | BSC | Vitality | S3 | Kronos Project | Lovwin |  |  | Initiated | 2015-02-10
2015-01-01 | Ilensys | BSC | Availaility | S1 | ECN and Agile Requests | Lovwin |  |  | Initiated | 2015-02-11
2015-02-01 | Ilensys | BSC | Availaility | S1 | ECN and Agile Requests | Lovwin |  |  | Initiated | 2015-03-02
2015-01-01 | Ilensys | BSC | IDO | S1 | BSC-SpeedVac Industrial Design | Mallikarujuna |  |  | Received | 2014-11-21 | 2015-01-07 | 6
2015-03-01 | Ilensys | BSC |  |  | B2 Cabinet | Lovwin |  |  | Received | 2015-03-04 | 2015-03-10 | 5
2015-03-01 | Cyient | BSC |  |  | Helios re-Layout | Subrahmanyaraju |  |  | Received | 2015-03-27 | 2015-03-29 | 6
2015-04-01 | Ilensys | BSC | Vitality | S3 | Kronos Project | Lovwin |  |  | Initiated | 2015-05-08
2015-06-15 | Ilensys | BSC | Vitality | S1 | Kronos-250L Outer Door Cabinet RAL pre Assembly 240L | Lovwin |  | Aulbach Holger | Initiated | 2015-07-15
2015-06-16 | Ilensys | BSC | Vitality | S1 | Kronos-Old-New Flaschendreher | Lovwin |  | Michael Albert | Initiated | 2015-07-15
2015-06-17 | Ilensys | BSC | Vitality | S1 | Kronos-Heaters door left and right 250l Kronos | Lovwin |  | Michael Albert | Initiated | 2015-07-15
2015-06-18 | Ilensys | BSC | Vitality | S1 | Kronos-HLA Documentation Change Glass Door | Lovwin |  | Barnkoth, Tino | Initiated | 2015-07-15
2015-06-19 | Ilensys | BSC | Vitality | S1 | Kronos-Packaging Parts for the 250l unit | Lovwin |  | Rainer Schuck | Initiated | 2015-07-15
2015-06-19 | Ilensys | BSC | Vitality | S1 | Kronos-Air guide Back wall | Lovwin |  | Fanta, Patrick | Received | 2015-07-15 | 2015-07-16 | 4
2015-06-19 | Ilensys | BSC | Vitality | S1 | Kronos-Glass Plate drawing updates | Lovwin |  | Zitzelsberger, Bettina | Initiated | 2015-07-15
2015-06-19 | Ilensys | BSC | Vitality | S1 | Goulash + Drawing Updates | Lovwin |  | Siffel, Chris | Initiated | 2015-07-15 | 2015-07-20 | 6
2015-06-19 | Ilensys | BSC | Vitality | S1 | ECN's & Agile requests | Lovwin |  | Derrick Smith | Initiated | 2015-07-15
2015-06-19 | Ilensys | BSC | Vitality | S1 | Drawing Updates | Lovwin |  | Siffel, Chris | Initiated | 2015-07-15 | 2015-07-20 | 6

## TC
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead |  | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-01-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q4-2014 | Vijesh |  | Newington | Received | 2015-01-12 | 2015-01-06 | 6
2015-02-01 | Ilensys |  |  | S1 | Work done on VT Cart | Vinay/Vijesh |  |  | Received | 2015-02-10 | 2015-02-23 | 6
2015-03-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Pat Horan | Newington | Initiated | 2015-04-21
2015-03-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Aaron Todd | Newington | Initiated | 2015-04-21
2015-03-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Sinclar | Newington | Initiated | 2015-04-21
2015-03-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Laura | Newington | Initiated | 2015-04-21
2015-03-01 | Ilensys | TC |  |  | Digital Manufacturing: TC Versa line- Phase 1 | Vijesh |  | Newington | Initiated | 2015-04-29
2015-05-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Pat Horan | Newington | Received | 2015-04-21 | 2015-05-05 | 7
2015-05-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Aaron Todd | Newington | Received | 2015-04-21 | 2015-05-05 | 5
2015-05-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Sinclar | Newington | Received | 2015-04-21 | 2015-05-05 | 7
2015-05-01 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q1-2015 | Vijesh | Laura | Newington | Received | 2015-04-21 | 2015-05-05 | 6
2015-06-15 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q2-2015 | Vijesh | Pelchat | Newington | Initiated | 2015-07-10 | 2015-07-21 | 6
2015-06-15 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q2-2015 | Vijesh | Aaron Todd | Newington | Initiated | 2015-07-10 | 2015-07-21 | 6
2015-06-15 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q2-2015 | Vijesh | Sinclar | Newington | Initiated | 2015-07-10 | 2015-07-21 | 4
2015-06-15 | Ilensys | TC | CAD | S1 | CAD support (Work Packages) /ECR-ECO creation : Q2-2015 | Vijesh | Laura | Newington | Initiated | 2015-07-10 | 2015-07-21 | 6
2015-06-15 | Ilensys | TC | Component Management | S1 | Component Management | Vijesh | John |  | Initiated | 2015-07-12 | 2015-07-21 | 6
2015-06-15 | Ilensys | TC |  |  | Digital Manufacturing: TC Versa line- Phase 1 | Vijesh |  | Newington | Received | 2015-04-29 | 2015-06-02 | 6
Note on A4: Initiated 1 CAS but Received 4 Feedback

## MM
Month | Vendor | Business Unit | Program/WP |  | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-01-01 | Cyient | MM | Quality | S1 | Schematic layout development | Srikanth G | Willmington | Received | 2015-01-09 | 2015-01-16 | 7
2015-01-01 | Cyient | MM | Quality | S1 | Schematic layout development | Srikanth G | Willmington | Received | 2015-01-09 | 2015-01-16 | 7
2015-01-01 | Cyient | MM | Quality | S1 | PCAD to Altum conv_TFS Adelade_Aus_India | Srikanth G | Adelaide | Received | 2015-01-13 | 2015-01-13 | 7
2015-02-15 | iLensys | MM | IDO | S1 | WP - 1026 | Mallikarjun | ECB | Received | 2015-02-04 | 2015-02-17 | 7
2015-02-15 | Ilensys | MM | CAD | S1 | Work done for Dec'14 & Jan'15 Months | Vinay | Willmington | Received | 2015-02-17 | 2015-02-28 | 7
2015-02-15 | Ilensys | MM | AVAILABILITY | S1 | Work done for June'14 to Jan'15 | Vinay | Willmington | Received | 2015-02-17 | 2015-02-28 | 7
2015-02-15 | Ilensys | MM | CAD | S1 | Work done for Dec'14 & Jan'15 Months | Vinay | ECB | Received | 2015-02-17 | 2015-02-28 | 7
2015-03-01 | Ilensys | MM | CAD | S1 | Work done for Q1 | Vinay | Adelaide | Received | 2015-04-21 | 2015-04-22 | 7
2015-03-01 | Ilensys | MM | CAD | S1 | Work done for Q1 | Vinay | Willmington | Initiated | 2015-04-21 | 2015-05-07 | 7
2015-03-01 | Ilensys | MM | CAD | S1 | Work done for Q1 | Vinay | MIN | Initiated | 2015-04-21
2015-03-01 | Ilensys | MM | CAD | S1 | Work done for Q1 | Vinay | ECB | Initiated | 2015-04-21
2015-03-01 | Cyient | MM | CAD | S1 | Schematic layout development | Srikanth G | Willmington | Initiated | 2015-04-21 | 2015-05-07 | 6
2015-03-01 | Cyient | MM | CAD | S1 | PCAD to Altum conv_TFS Adelade_Aus_India | Srikanth G | Adelaide | Initiated | 2015-04-21
2015-03-01 | Cyient | MM | Vitality | S3 | MiniZAP30 | Srikanth G |  | Received | 2015-04-20 | 2015-05-20 | 7
2015-03-01 | Ilensys | MM | AVAILABILITY | S1 | Work done for Q1 | Vinay | Willmington | Received | 2015-04-24 | 2015-05-02 | 7
2015-03-01 | Ilensys | MM | AVAILABILITY | S1 | Work done for Q1 | Vinay | ECB | Received | 2015-04-24 | 2015-05-12 | 6
2015-06-15 | Ilensys | MM | CAD | S1 | Work done for Q2 | Vinay | Adelaide | Initiated | 2015-07-10
2015-06-15 | Ilensys | MM | CAD | S1 | Work done for Q2 | Vinay | Willmington | Received | 2015-07-10 | 2015-07-13 | 7
2015-06-15 | Ilensys | MM | CAD | S1 | Work done for Q2 | Vinay | MIN | Initiated | 2015-07-10 | 2015-07-15 | 4
2015-06-15 | Ilensys | MM | CAD | S1 | Work done for Q2 | Vinay | ECB | Initiated | 2015-07-10
2015-06-15 | Ilensys | MM | AVAILABILITY | S1 | Work done for Q2 | Vinay | Willmington | Received | 2015-07-10 | 2015-07-13 | 7
2015-06-15 | Cyient | MM | CAD | S1 | Schematic layout development | Srikanth G | Willmington | Initiated | 2015-07-21
2015-06-15 | Cyient | MM | CAD | S1 | PCAD to Altum conv_TFS Adelade_Aus_India | Srikanth G | Adelaide | Initiated | 2015-07-21
2015-06-15 | Cyient | MM | Vitality | S3 | MiniZAP30 | Srikanth G |  | Initiated | 2015-07-21
2015-07-15 | Cyient | MM | CAD | S1 | PCAD to Altum conv_TFS Adelade_Aus_India | Srikanth G | Adelaide | Received | 2015-07-21 | 2015-08-04 | 4

## PAI
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-01-01 | BAT | PAI |  |  | Trunarc-Japanese software release, 1.4.1 | Uma Oswal |  | Received | 2015-01-19 | 2015-01-19 | 6
2015-01-01 | Ilensys | PAI | IDO | S1 | PAI- XL5-CMF | Mallikarujuna |  | Received | 2014-12-07 | 2015-01-05 | 6
2015-03-01 | Ilensys | PAI | CAD | S1 | CAD support for Q1 | Vijesh |  | Initiated | 2015-04-21
2015-03-01 | BAT | PAI |  |  | MicroPAHZIR EOL | Shirish Kulkarni |  | Received | 2015-04-03 | 2015-04-21 | 6
2015-03-01 | Ilensys | PAI | IDO | S1 | PAI-LTS | Mallikarujuna |  | Initiated | 2015-04-29
2015-03-01 | Ilensys | PAI | User App | S1 | PAI-Interactive App | Karthik |  | Received | 2015-03-12 | 2015-03-12 | 5
2015-05-15 | BAT | PAI |  |  | TruNarc 1.5 software testing | Uma Oswal |  | Received | 2015-05-21 | 2015-05-22 | 5
2015-06-15 | BAT | PAI |  |  | TruNarc 1.5 software testing | Uma Oswal |  | Received | 2015-05-21 | 2015-06-03 | 6
2015-06-15 | Ilensys | PAI | CAD/IDO | S1 | CAD support for Q2 | Vijesh |  | Initiated | 2015-07-17

## RMSI
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-03-01 | Ilensys | RMSI | CAD | S1 | CAD support for Q1 | Vijesh |  | Initiated | 2015-04-21
2015-03-01 | Ilensys | RMSI | IDO | S1 | EPD-Phoenix Dosimetre | Mallikarjun |  | Initiated | 2015-04-21
2015-06-15 | Ilensys | RMSI | IDO | S1 | EPD-Dosimetre-Desktop reader | Mallikarjun |  | Initiated | 2015-06-26
2015-06-15 | Ilensys | RMSI | CAD | S1 | CAD support for Q2 | Vijesh |  | Initiated | 2015-07-10

## BPP
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-02-15 | Ilensys | BPP | CAD | S1 | Work done on BIN Drawings & reporting till now | Vinay | Logan | Received | 2015-02-17 | 2015-02-18 | 5
2015-03-15 | Ilensys | BPP | CAD | S1 | BIN Drawings | Vinay | Logan | Received | 2015-04-17 | 2015-04-17 | 6

## WAI
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
2015-03-01 | iLensys | WAI | CAD | S1 | Updating of 5 drawings | Lovwin |  | Initiated | 2015-03-30
2015-05-15 | iLensys | WAI | Manuals | S1 |  | Lovwin |  | Initiated | 2015-05-18
2015-06-15 | iLensys | WAI | Manuals | S1 |  | Lovwin |  | Received | 2015-05-18 | 2015-06-10 | 7
2015-08-15 | iLensys | WAI | CAD | S1 | Updating of 5 drawings | Lovwin |  | Initiated | 2015-08-24

## Centrifugation
Month | Vendor | Business Unit | Program/WP | Category | Project name | project lead | Site | CF Status | Requested date | Received date | CAS Score | Attachments
May | iLensys | Centrifugation | CAD | S1 | CAD | Lovwin |  | Received | 2015-05-18 | 2015-05-20 | 7

## Sheet2
Month | BU | Category | Score
Jan | CS | CAD | 6
Jan | CS | Special project | 5 | Score | 4
Jan | MM | CAD | 7
Jan | MM | CAD | 7 | Count of Category | Column Labels
Jan | MM | CAD | 7 | Row Labels | Feb | Mar | May | Jun | Jul | Grand Total
Jan | TC | CAD | 6 | BSC |  |  |  | 1 |  | 1
Jan | PAI | IDO | 6 | CS | 1 | 1 | 1 |  |  | 3
Jan | PAI | CAD | 6 | MM |  |  |  | 1 | 1 | 2
Jan | BSC | IDO | 6 | TC |  |  |  | 1 |  | 1
Feb | CS | CAD | 4 | Grand Total | 1 | 1 | 1 | 3 | 1 | 7
Feb | CS | Data Analytics | 7
Feb | CS | Data Analytics | 7
Feb | BPP | CAD | 5
Mar | CS | CAD | 6 | Score | 5
Mar | CS | CAD | 5
Mar | CS | Data Analytics | 7 | Count of Category | Column Labels
Mar | CS | Data Analytics | 6 | Row Labels | Jan | Feb | Mar | May | Aug | Grand Total
Mar | CS | Vitality | 6 | BPP |  | 1 |  |  |  | 1
Mar | CS | Vitality | 4 | BSC |  |  | 1 |  |  | 1
Mar | CS | Vitality | 7 | CS | 1 |  | 1 |  | 1 | 3
Mar | MM | CAD | 7 | PAI |  |  | 1 | 1 |  | 2
Mar | PAI | Vitality | 6 | TC |  |  |  | 1 |  | 1
Mar | PAI | User App | 5 | Grand Total | 1 | 1 | 3 | 2 | 1 | 8
Mar | BPP | CAD | 6
Mar | BSC | CAD | 6
Mar | BSC | CAD | 5 | Score | 6
Apr | CS | CAD | 6
Apr | CS | CAD | 6 | Count of Category | Column Labels
Apr | CS | Data Analytics | 7 | Row Labels | Jan | Mar | Apr | May | Jun | Jul | Sep | Grand Total
Apr | CS | Data Analytics | 7 | BPP | [7 empty] | 1 | bar: Column Labels Mar
Apr | CS | Quality | 6 | BSC | Column Labels Jan: 1; Column Labels Mar: 1; Column Labels Jun: 2 | 4
May | CS | CAD | 6 | CAD | [7 empty] | 1 | bar: Column Labels Sep
May | CS | CAD | 7 | CS | 1 | 3 | 3 | 2 | 1 | 1 |  | 11
May | CS | Techpub | 6 | Data Analytics | [7 empty] | 1 | bar: Column Labels Sep
May | CS | Data Analytics | 7 | MM | Column Labels May: 2 | 2
May | CS | MCTO | 4 | PAI | Column Labels Jan: 2; Column Labels Mar: 1; Column Labels Jun: 1 | 4
May | MM | CAD | 7 | TC | Column Labels Jan: 1; Column Labels May: 1; Column Labels Jun: 5 | 7
May | MM | Availability | 7 | VHEN | [7 empty] | 1 | bar: Column Labels Sep
May | MM | Availability | 6 | Grand Total | 5 | 6 | 3 | 5 | 9 | 1 | 3 | 32
May | MM | CAD | 6
May | MM | Vitality | 7
May | TC | CAD | 7 | Score | Column Labels Jan: 7
May | TC | CAD | 5
May | TC | CAD | 7 | Count of Category | Column Labels Jan: Column Labels
May | TC | CAD | 6 | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Grand Total
May | PAI | CAD | 5 | Centrifugation | [6 empty] | 1 | bar: Column Labels May
May | Centrifugation | CAD | 7 | CS |  | 2 | 2 | 2 | 2 | 1 | 9
Jun | CS | Vitality | 6 | MM | 3 |  | 1 |  | 3 | 2 | 9
Jun | CS | Vitality | 7 | TC | Column Labels May: 2 | 2
Jun | MM | CAD | 7 | WAI | [6 empty] | 1 | bar: Column Labels Jun
Jun | MM | Availability | 7 | Grand Total | 3 | 2 | 3 | 2 | 8 | 4 | 22
Jun | MM | CAD | 4
Jun | TC | CAD | 6
Jun | TC | CAD | 6
Jun | TC | CAD | 4 | CAS | Column Labels Jan: Count of Score
Jun | TC | CAD | 6 | unacceptable | Column Labels Jan: 0
Jun | TC | Availability | 6 | 2 | Column Labels Jan: 0
Jun | TC | CAD | 6 | 3 | Column Labels Jan: 0
Jun | PAI | CAD | 6 | 4 | Column Labels Jan: 7
Jun | BSC | CAD | 4 | 5 | Column Labels Jan: 8
Jun | BSC | CAD | 6 | 6 | Column Labels Jan: 32
Jun | BSC | CAD | 6 | Ext Satisfied | Column Labels Jan: 22
Jun | WAI | Techpub | 7
Jul | CS | Data Analytics | 6
Jul | MM | CAD | 4
Aug | CS | User App | 5
Sep | CAD | CAD | 6
Sep | Data Analytics | Data Analytics | 6
Sep | VHEN | VHEN | 6